## Sheet1
Project Info | Hourly Rate ($/hr.) |  | References | Total Project Budget | 183772
Title: Project Budget and Resource Allocation | Project Manager | 37 | Project Manager I - Hourly Rate | Start Date: | 2020-07-11
Organization: Northeastern University | Resource Manager | 23 | Resource Manager - Hourly Rate | End Date: | 2020-02-26
Project Name: Library Seat Availability Checking (LSAC) System | Hardware Consultant | 71 | Hardware Engineer Consultant - Hourly Rate
| Software Consultant | 73 | Software Engineer Consultant - Hourly Rate
| Budget Coordinator | 23 | Budget Coordinator Salary - Hourly Rate
Steps | Labor |  |  |  |  | Fixed Cost (Travel, Material, Stationary, Miscellaneous) | Overall Estimated Budget | Notes (if any)
| Duration (Days) | Duration( Hours) | Responsibility | No of employee associated | Total Labor Cost ($) | Note: Estimating 10% of Total Labor Costs is Fixed Cost | Total Labor Cost+ Fixed Cost | Add notes for tasks that includes only Fixed cost
1.0 Project Initiation Phase
1.1 Project launch meeting
1.1.1 Define objective and goal of the project | 2 | 16 | Project Manager | 1 | 592 | 59 | 651
1.1.2 Document project stakeholder | 2 | 16 | Project Manager | 1 | 592 | 59 | 651
1.2 Form project team and assign roles
1.2.1 Team formation and role assignment | 3 | 24 | Project Manager, Resource Manager | 2 | 1440 | 88 | 1528
1.3 Project Charter Development
1.3.1 Project scope statement | 2 | 16 | Project Manager, Budget Coordinator | 1 | 736 | 36 | 772
2.0 Project Planning Phase
2.1 Project Plan Development
2.1.1 Identity issues in current system using surveys | 4 | 32 | Hardware and Software Consultant | 2 | 4608 | 227 | 4835
2.1.2 Work breakdown structure (WBS) | 3 | 24 | Project Manager, Resource Manager | 2 | 1440 | 144 | 1584
2.2 Define project requirements
2.2.1 Gather user requirement | 7 | 56 | Hardware and Software Consultant | 2 | 8064 | 649 | 8713
2.2.2 Build system requirement | 8 | 64 | Hardware and Software Consultant | 2 | 9216 | 742 | 9958
2.3 Resource management
2.3.1 Resource allocation | 8 | 64 | Resource Manager, Budget Coordinator | 2 | 2944 | 147 | 3091
2.4 Vendor evaluation and hardware procurement
2.4.1 Identity potential vendor for the project resources | 10 | 80 | Resource Manager, Budget Coordinator | 2 | 3680 | 184 | 3864
2.4.2 Finalize vendor and sign the contract | 11 | 88 | Resource Manager, Budget Coordinator | 2 | 4048 | 202 | 4250
2.4.3 Sensor and Hardware materials | [5 empty] | 4000 | 4000 | Fixed Cost for Sensor and Hardware requirements
3.0 Project Execution Phase
3.1 System design
3.1.1 System design for web application | 12 | 96 | Software Consultant | 1 | 7008 | 432 | 7440
3.1.2 System design for mobile application | 9 | 72 | Software Consultant | 1 | 5256 | 324 | 5580
3.1.3 UI design ( web+ mobile) | 7 | 56 | Software Consultant | 1 | 4088 | 252 | 4340
3.2 Assemble hardware requirement
3.2.1 Design hardware | 8 | 96 | Hardware Consultant | 1 | 6816 | 681 | 7497
3.2.2 Hardware implementation | 7 | 56 | Hardware Consultant | 1 | 3976 | 397 | 4373
3.2.3 Resource management | 10 | 80 | Hardware Consultant | 1 | 5680 | 568 | 6248
3.3 Software Development
3.3.1 Develop web application (Enhanced) | 27 | 216 | Software Consultant | 1 | 15768 | 972 | 16740
3.3.2 Develop mobile application | 17 | 136 | Software Consultant | 1 | 9928 | 612 | 10540
3.4 Testing
3.4.1 Unit testing | 10 | 80 | Hardware and Software Consultant | 2 | 11520 | 928 | 12448
3.4.2 Integration testing | 10 | 80 | Hardware and Software Consultant | 2 | 11520 | 928 | 12448
3.4.3 Regression testing | 8 | 64 | Hardware and Software Consultant | 2 | 9216 | 742 | 9958
4.0 Project Closing Phase
4.1 Management and control
4.1.1 Monitor glitches and system performance | 18 | 144 | Project Manager, Hardware and Software Consultant | 3 | 26064 | 2203 | 28267
4.2 Project rollout
4.2.1 Launch project (Lesson Learned review) | 5 | 40 | Project Manager, Budget Coordinator, and Resource Manager | 3 | 3320 | 332 | 3652
4.2.2 Confirm project completion and release resources | 2 | 16 | Project Manager, Budget Coordinator, and Resource Manager | 3 | 1328 | 132 | 1460
4.3 Establish process for archiving project data
4.3.1 Archive documents | 10 | 80 | Project Manager and Resource Manager | 2 | 4800 | 480 | 5280
4.4 Prepare final reports
4.4.1 Publish final report to all stakeholders | 5 | 64 | Project Manager | 1 | 2368 | 236 | 2604
4.4.2 Celebrate and project completion party | [5 empty] | 1000 | 1000 | Assuming Fixed Cost of $1,000 for celebration
Total | 225 | 1856 |  | 45 | 166016 | 17756 | 183772
183772