## Sheet1
Title: RACI Chart
Organization: Northeastern University
Project Name: Library Seat Availability Checking (LSAC) System
Steps | Responsibility | Karan (Project Manager) | Implementation Lead (Northeastery University) | Shiv (Resource Manager) | Vedant (Lead Software Engineer) | Vijayakumar ( Lead Hardware Engineer) | Zecheng (Budget Coordinator) | Library Director (Northeastern University) | IT Director (Northeastern University) | President (Northeastern University )
1.0 Project Initiation Phase
1.1 Project launch meeting
1.1.1 Define objective and goal of the project | Project Manager | R
1.1.2 Document project stakeholder | Project Manager | R
1.2 Form project team and assign roles
1.2.1 Team formation and role assignment | Project Manager | R
1.3 Project Charter Development
1.3.1 Project scope statement | Budget Coordinator | [5 empty] | R
2.0 Project Planning Phase
2.1 Project Plan Development
2.1.1 Identity issues in current system using surveys | Hardware Consultants |  |  |  | A | R
2.1.2 Work breakdown structure (WBS) | Project Manager and Team | R
2.2 Define project requirements
2.2.1 Gather user requirement | Hardware and Software Consultants |  |  |  | R | R
2.2.2 Build system requirement | Hardware and Software Consultants |  |  |  | R | R
2.3 Resource management | [8 empty] | I
2.3.1 Resource allocation | Resource Manager |  |  | R
2.4 Vendor evaluation and hardware procurement
2.4.1 Identity potential vendor for the project resources | Budget Coordinator | [5 empty] | R
2.4.2 Finalize vendor and sign the contract | Budget Coordinator | [5 empty] | R
3.0 Project Execution Phase
3.1 System design
3.1.1 System design for web application | Software Consultant |  |  |  | R
3.1.2 System design for mobile application | Software Consultant |  |  |  | R
3.1.3 UI design ( web+ mobile) | Software Consultant |  |  |  | R
3.2 Assemble hardware requirement
3.2.1 Design hardware | Hardware Consultant |  |  |  |  | R
3.2.2 Hardware implementation | Hardware Consultant |  |  |  |  | R
3.2.3 Resource management | Hardware Consultant |  |  |  |  | R
3.3 Software Development
3.3.1 Develop web application (Enhanced) | Software Consultant |  |  |  | R
3.3.2 Develop mobile application | Software Consultant |  |  |  | R
3.4 Testing
3.4.1 Unit testing | Hardware and Software Consultants |  |  |  | R | R
3.4.2 Integration testing | Hardware and Software Consultants |  |  |  | R | R
3.4.3 Regression testing | Hardware and Software Consultants |  |  |  | R | R
4.0 Project Closing Phase
4.1 Management and control
4.1.1 Monitor glitches and system performance | Project Manager and Consultants | R |  |  | R | R |  |  | C | C
4.2 Project rollout
4.2.1 Launch project (Lesson Learned review) | Project Team, President | [7 empty] | R | R
4.3 Establish process for archiving project data
4.3.1 Archive documents | Library Director | [6 empty] | I | I | I
4.4 Prepare final reports
4.4.1 Publish final report to all stakeholders | Project Manager and Team | R