## Sheet1
Title: Work Breakdown Structure (WBS)
Organization: Northeastern University
Project Name: Library Seat Availability Checking (LSAC) System
Steps | Responsibility | Precedents | Duration (Days) | Start Date (mm/dd/yyyy) | End Date (mm/dd/yyyy)
1.0 Project Initiation Phase
1.1 Project launch meeting
1.1.1 Define objective and goal of the project | Project Manager | - | 2 | 2020-07-11 | 2020-07-13
1.1.2 Document project stakeholder | Project Manager | 1.1.1 | 2 | 2020-07-13 | 2020-07-15
1.2 Form project team and assign roles
1.2.1 Team formation and role assignment | Project Manager | 1.1.2 | 3 | 2020-07-15 | 2020-07-18
1.3 Project Charter Development
1.3.1 Project scope statement | Sponsor | 1.1.1 | 2 | 2020-07-18 | 2020-07-20
2.0 Project Planning Phase
2.1 Project Plan Development
2.1.1 Identity issues in current system using surveys | Hardware and Software Consultants | 1.3.1 | 4 | 2020-07-20 | 2020-07-24
2.1.2 Work breakdown structure (WBS) | Project Manager and Team | 1.1.2 | 3 | 2020-07-24 | 2020-07-27
2.2 Define project requirements
2.2.1 Gather user requirement | Hardware and Software Consultants | 2.1.1 | 7 | 2020-07-27 | 2020-08-03
2.2.2 Build system requirement | Hardware and Software Consultants | 2.1.1 | 8 | 2020-08-03 | 2020-08-11
2.3 Resource management
2.3.1 Resource allocation | Resource Manager | 2.1.2 | 8 | 2020-08-11 | 2020-08-19
2.4 Vendor evaluation and hardware procurement
2.4.1 Identity potential vendor for the project resources | Budget Coordinator | 2.3.1 | 10 | 2020-08-19 | 2020-08-29
2.4.2 Finalize vendor and sign the contract | Budget Coordinator | 2.4.1 | 11 | 2020-08-29 | 2020-09-09
3.0 Project Execution Phase
3.1 System design
3.1.1 System design for web application | Software Consultant | 2.2.2 | 12 | 2020-09-09 | 2020-09-21
3.1.2 System design for mobile application | Software Consultant | 2.2.2 | 9 | 2020-09-21 | 2020-09-30
3.1.3 UI design ( web+ mobile) | Software Consultant | 3.1.1 & 3.1.2 | 7 | 2020-09-30 | 2020-10-07
3.2 Assemble hardware requirement
3.2.1 Design hardware implementation | Hardware Consultant | 2.2.2 | 20 | 2020-10-07 | 2020-10-27
3.2.2 Resource management | Hardware Consultant | 2.2.1 | 10 | 2020-10-27 | 2020-11-06
3.3 Software Development
3.3.1 Develop web application (Enhanced) | Software Consultant | 3.1.1 | 27 | 2020-11-06 | 2020-12-03
3.3.2 Develop mobile application | Software Consultant | 3.1.2 | 17 | 2020-12-03 | 2020-12-20
3.4 Testing
3.4.1 Unit testing | Hardware and Software Consultants | 3.3.1 | 10 | 2020-12-20 | 2020-12-30
3.4.2 Integration testing | Hardware and Software Consultants | 3.3.2 | 10 | 2020-12-30 | 2021-01-09
3.4.3 Regression testing | Hardware and Software Consultants | 3.3.1 & 3.3.2 | 8 | 2021-01-09 | 2021-01-17
4.0 Project Closing Phase
4.1 Management and Control
4.1.1 Monitor glitches and system performance | Project Manager and Consultants | 3.4.1, 3.4.2 & 3.4.3 | 18 | 2021-01-17 | 2021-02-04
4.2 Project Rollout
4.2.1 Launch project (Lesson Learned review) | Project Team, President, Sponsor | 4.1.1 | 7 | 2021-02-04 | 2021-02-11
4.3 Establish process for archiving project data
4.3.1 Archive documents | Library Director | 4.2.1 | 10 | 2021-02-11 | 2021-02-21
4.4 Prepare final reports
4.4.1 Publish final report to all stakeholders | Project Manager and Team | 4.3.1 | 5 | 2021-02-21 | 2021-02-26